## MRD PLAN
Plan Order Material Control (ZS11)
Project : ABT-TSRA
1). Plan ship ZS11 Due |  | 02 Mar '2020 | 2020-03-02 | [9 empty] | Summary (PCS) | 480 | Plan | Actual | Percent% |  | Plan | Actual | Percent% |  | Plan | Actual | Percent% |  | Plan | Actual | Percent% |  | Plan | Actual | Percent% |  | Albatross Logistics Co., Ltd.
2). Packing Plan ZS11 Due |  | 29 Feb '2020 | 2020-02-29 | [9 empty] | Plan (Set) | 480 | 488 | 0 | 0% |  | 0 | 0 | 0% |  | 0 | 0 | 0% |  | 0 | 0 | 0% |  | 0 | 0 | 0% |  | 336/7 M.7 T.Bowin A.Sriracha Chonuri 20230
3). Plan Delivery Mat. Date : |  | 28 Feb '2020 | 2020-02-28 | [9 empty] | Actual (Set) | 0 | [23 empty] | *TSRA_ZS11-20200219-001*
MRD. | TSRA_ZS11-20200219-001 | [11 empty] | Actual (%) | 0% | Qty' Part | Plan (Mat) | Rec (Mat) |  | Qty' Part | Plan (Mat) | Rec (Mat) |  | Qty' Part | Plan (Mat) | Rec (Mat) |  | Qty' Part | Plan (Mat) | Rec (Mat) |  | Qty' Part | Plan (Mat) | Rec (Mat) |  |  |  | MRD TSRA Number : | TSRA_ZS11-20200219-001
Item | Part no. | Supplier | Package (Code) (MM.) | SNP | Unit load | Insert No. | Pad | Cover | Ship Code | Packing Line | Forcast Next Week | Plan Pack_Q'ty | Qty Set | Delivery Plan | 2020-02-28 | Plan (Set) | 2020-02-27 | Dift | 2020-02-29 | Plan (Set) | 2020-02-28 | Dift | 2020-03-01 | Plan (Set) | 2020-02-29 | Dift | 2020-03-02 | Plan (Set) | 2020-03-01 | Dift | 2020-03-03 | Plan (Set) | 2020-03-02 | Dift | Summary Q'ty / Week | Rec/(Set)/Week | Balance (Set) | Remark : หมายเหตุ
1 | 10336751-SPRP | SRCP | FOT1730X880X560 | 1 | 1 | No Insert | 0 | 0 | MGST | 1 | 0 | 28 | 28 | 28 Feb '2020 | 28 | 28 |  | -28 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 28 | 0 | -28
2 | 10349819-SPRP | SRCP | FOT1240X250X200 | 1 | 1 | No Insert | 0 | 0 | MGST | 1 | 0 | 50 | 50 | 28 Feb '2020 | 50 | 50 |  | -50 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 50 | 0 | -50
3 | 10338991-SPRP | SRCP | IMC010 | 1 | 1 | No Insert | 0 | 0 | MGST | 1 | 0 | 8 | 8 | 28 Feb '2020 | 8 | 8 |  | -8 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 8 | 0 | -8
4 | 10344162-SPRP | UK | FOT1690X630X670 | 1 | 1 | No Insert | 0 | 0 | MGST | 1 | 0 | 50 | 50 | 28 Feb '2020 | 50 | 50 |  | -50 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 50 | 0 | -50
5 | 10343984 | SRCP | FOT1840X360X600 | 1 | 1 | No Insert | 0 | 0 | MGST | 1 | 0 | 50 | 50 | 28 Feb '2020 | 50 | 50 |  | -50 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 50 | 0 | -50
6 | 10344164 | SRCP | FOT1800X330X390 | 1 | 1 | No Insert | 0 | 0 | MGST | 1 | 0 | 70 | 70 | 28 Feb '2020 | 70 | 70 |  | -70 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 70 | 0 | -70
7 | 10336894 | SRCP | FOT1240X250X200 | 1 | 1 | No Insert | 0 | 0 | MGST | 1 | 0 | 98 | 98 | 28 Feb '2020 | 98 | 98 |  | -98 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 98 | 0 | -98
8 | 10348157 | SRCP | FOT1240X250X200 | 1 | 1 | No Insert | 0 | 0 | MGST | 1 | 0 | 21 | 21 | 28 Feb '2020 | 21 | 21 |  | -21 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 21 | 0 | -21
9 | 10361127 | SRCP | FOT1240X250X200 | 1 | 1 | No Insert | 0 | 0 | MGST | 1 | 0 | 58 | 58 | 28 Feb '2020 | 58 | 58 |  | -58 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 58 | 0 | -58
10 | 10344260 | SRCP | IMC010 | 1 | 1 | No Insert | 0 | 0 | MGST | 1 | 0 | 7 | 7 | 28 Feb '2020 | 7 | 7 |  | -7 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 7 | 0 | -7
11 | 10345448 | SRCP | IMC010 | 1 | 1 | No Insert | 0 | 0 | MGST | 1 | 0 | 2 | 2 | 28 Feb '2020 | 2 | 2 |  | -2 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2 | 0 | -2
12 | 10343137 | SRCP | IMC010 | 1 | 1 | No Insert | 0 | 0 | MGST | 1 | 0 | 2 | 2 | 28 Feb '2020 | 2 | 2 |  | -2 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2 | 0 | -2
13 | 10345485 | SRCP | IMC010 | 1 | 1 | No Insert | 0 | 0 | MGST | 1 | 0 | 2 | 2 | 28 Feb '2020 | 2 | 2 |  | -2 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2 | 0 | -2
14 | 10343976 | SRCP | IMC010 | 1 | 1 | No Insert | 0 | 0 | MGST | 1 | 0 | 2 | 2 | 28 Feb '2020 | 2 | 2 |  | -2 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2 | 0 | -2
15 | 10454616 | PMM | FOT790X230X150 | 1 | - | No Insert | 0 | 0 | MGST | - | 0 | 2 | 2 | 28 Feb '2020 | 2 | 2 |  | -2 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2 | 0 | -2
16 | 10454605 | SRCP | IMC050 | 1 | 1 | No Insert | 0 | 0 | MGST | 1 | 0 | 2 | 2 | 28 Feb '2020 | 2 | 2 |  | -2 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2 | 0 | -2
17 | 10454606 | SRCP | IMC050 | 1 | 1 | No Insert | 0 | 0 | MGST | 1 | 0 | 2 | 2 | 28 Feb '2020 | 2 | 2 |  | -2 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2 | 0 | -2
18 | 10454603 | SRCP | IMC133 | 1 | 1 | No Insert | 0 | 0 | MGST | 1 | 0 | 6 | 6 | 28 Feb '2020 | 6 | 6 |  | -6 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6 | 0 | -6
19 | 10454604 | SRCP | IMC133 | 1 | 1 | No Insert | 0 | 0 | MGST | 1 | 0 | 9 | 9 | 28 Feb '2020 | 9 | 9 |  | -9 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9 | 0 | -9
20 | 10230145 | SRCP | IMC130 | 1 | 1 | No Insert | 0 | 0 | MGST | 1 | 0 | 5 | 5 | 28 Feb '2020 | 5 | 5 |  | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 5 | 0 | -5
21 | 10251283 | SRCP | IMC010 | 1 | 1 | No Insert | 0 | 0 | MGST | 1 | 0 | 2 | 2 | 28 Feb '2020 | 2 | 2 |  | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2 | 0 | -2
22 | 10251284 | SRCP | IMC010 | 1 | 1 | No Insert | 0 | 0 | MGST | 1 | 0 | 2 | 2 | 28 Feb '2020 | 2 | 2 |  | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2 | 0 | -2
23 | 10360709 | SRCP | IMC010 | 1 | 1 | No Insert | 0 | 0 | MGST | 1 | 0 | 2 | 2 | 28 Feb '2020 | 2 | 2 |  | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2 | 0 | -2